# GEO MCP Server

Next Gates Developer Plan

30 September 2026 | Gate C.5, D and E handoff

The automated VS Code path completes the 23-operation synthetic journey, reconnects after restart and sits on a 612-test green baseline. Close the interactive Copilot trust check before Gate D. Do not redesign the workflow or weaken its human controls.

# Planning Framework

| Section | Description | Notes |
| --- | --- | --- |
| Startle | The automated Copilot-equivalent flow passes on a 612-test green baseline; only the interactive VS Code trust and Copilot check remains in Gate C.5. | Repeat the workload through the actual hosted topology. |
| WIIFM | A shared MCP endpoint gives local and hosted agents the governed GEO workflow already used by humans. | Agents gain tools without gaining human approval rights. |
| Needs and Challenges | Remote use needs real identity, PostgreSQL, durable artifacts, secure browser sessions, worker isolation and observability. | The loopback bearer setup is development-only. |
| Define Questions | Can the same server preserve isolation and responsiveness remotely, then complete one- and three-profile live runs with exact accounting? | Gate C.5 closes local usability. Gate D proves remote readiness. Gate E proves live acceptance. |
| Cornerstone | Finish and stabilise the existing bounded asynchronous workflow before productionising it. | REST, UI and MCP continue to share one service and job model. |
| Supporting Evidence 1 | All 20 tools work over real stdio and Streamable HTTP clients. | Submission returns durable job IDs and discovery starts no provider work. |
| Supporting Evidence 2 | Lease, replay, checkpoint, queue, migration and export races have regression tests. | All 58 MCP and human-handoff tests pass; the complete repository suite passes 612 tests with 18 existing serialization warnings. |
| Supporting Evidence 3 | Five-client, 1,000-run local performance passes every payload and latency gate. | Stdio p95 19 ms; HTTP p95 117 ms; catalogue 17,970 bytes; maximum response 4,982 bytes. |
| Repeat Cornerstone | Close the interactive local check, then harden the same workflow for shared use. | Preserve human approval, evidence semantics and provider accounting. |
| Conclusion and next steps | Complete the interactive Gate C.5 check before an approved Gate D deployment. | Stop if isolation, migrations, remote p95 or live completion experience fails. |

# Current Baseline

| Gate | Status | Evidence |
| --- | --- | --- |
| A. SDK and contract | Complete | mcp==2.2.0, 20 tools, real stdio and HTTP clients, structured results. |
| B. Governance parity | Complete locally | Six stages, human query approval, agent stage authorisation, owner isolation and 23-operation mock flow. |
| C/C.5 Local performance and VS Code | Automated proof complete; interactive pending | 20-tool workspace discovery, full synthetic handoff, restart proof, five clients, 1,000 runs and 200 calls per transport. |
| D. Remote readiness | Not started | Needs approved hosting, Entra/OAuth, PostgreSQL, durable artifacts, web security and remote proof. |
| E. Live canary | Blocked | Needs Gate D pass plus explicit URL, roster, operation allowance, cost and retention approval. |

| Measure | stdio | Streamable HTTP | Target |
| --- | --- | --- | --- |
| Warm p95 | 19 ms | 117 ms | At most 2 seconds |
| Maximum duration | 136 ms | 169 ms | Reported separately |
| Maximum response | 4,972 bytes | 4,982 bytes | Default at most 16 KiB |
| Catalogue | 17,970 bytes | 17,970 bytes | At most 32 KiB |

# Safety Boundaries

| Preserve | Required behaviour |
| --- | --- |
| Human authority | Exact-query approval and legacy draft decisions remain human-only. |
| Agent execution | Paid stages require owner/principal/run/revision/policy-bound human authorisation. |
| Admission | One active job, 20 globally queued jobs and four queued jobs per owner. |
| Provider accounting | Claim and charge before dispatch; no automatic retry; ambiguous attempts remain charged. |
| Evidence | Checkpoint validated output; retain provenance and failed-call coverage. |
| Exports | Freeze the main ZIP; version companion outputs; never send ZIP bytes or storage keys to the model. |
| Live switch | Keep GEO_MCP_ALLOW_LIVE false until Gate D passes and Gate E is authorised. |

# Gate D: Remote Deployment Readiness

| Phase | Work | Completion evidence |
| --- | --- | --- |
| D0 Decisions | Confirm hosting, region, Foundry consumer, Entra tenant/audience/scopes, PostgreSQL, artifact storage, network, providers and owners. | Approved architecture and ownership record before provisioning. |
| D1 Data | Inject PostgreSQL and durable ArtifactStorage configuration; exercise migrations 0004/0005 plus multi-instance races. | PostgreSQL integration tests, migration rehearsal, backup/restore and unchanged hashes. |
| D2 Identity | Use MCP SDK TokenVerifier/AuthSettings with Entra. Map delegated users and explicitly delegated app identities to owners. | Identity matrix for wrong owner, tenant, audience, expiry and missing scopes. |
| D3 Human web | Implement approved human sign-in, secure cookies, CSRF and explicit Host/Origin policy. | Negative CSRF tests, human/agent route separation and browser parity. |
| D4 Runtime | Deploy API and worker separately; use managed identity; add safe logs, traces, heartbeats and graceful replacement. | Restart/reconnect, lease recovery and no discovery side effects. |
| D5 Remote proof | Repeat five-client, 1,000-run, 200-call workload through real HTTPS and authentication. | Remote p95 and payload report plus queue-race evidence. |

Recommended starting topology: Azure Container Apps with one API application and one separately managed worker, subject to platform-owner approval. Do not provision a default when tenant, region, ingress, retention or ownership is unresolved.

# Gate D Acceptance

| Target | Required result |
| --- | --- |
| Warm p95 | At most 2 seconds including authentication, serialisation and remote network. |
| Payloads | Default at most 16 KiB; progress at most 8 KiB; details at most 64 KiB with continuation. |
| Catalogue | At most 32 KiB or the target client's stricter limit. |
| Isolation | No cross-owner tool, resource, cursor, cache, artifact, cancellation or protocol-session access. |
| Queue | One active, 20 globally queued and four per owner under concurrent REST and MCP submissions. |
| Read cost | Zero provider calls from discovery, status, results, evidence, reports or exports. |

# Gate E: Separately Authorised Live Canary

| Phase | Procedure | Stop rule |
| --- | --- | --- |
| E0 Authority | Record URL/domain, locale, roster, deployments, operation allowance, maximum cost, retention, time window and operator. | Do not reuse or mutate consumed grants. |
| E1 One profile | Run preparation plus five searches and five evaluations. Expected score-only ceiling: 13 operations. | Stop if access, accounting, evidence semantics, handoff or completion time is unsatisfactory. |
| E2 Three profiles | Reuse five ordered packets across 15 isolated evaluations. Expected score-only ceiling: 23 operations. | Do not claim three-profile readiness unless every deployment is verified. |
| E3 Decision | Compare control and provider latency, token use, errors, charged counts, coverage and output parity. | Choose shared, narrowed, read-only or stopped mode. Fast submission alone is not success. |

# Developer Work Order

| ID | Work | Depends on |
| --- | --- | --- |
| remote-decisions | Approve hosting, identity, data, network, provider and ownership decisions. | Interactive Gate C.5 |
| postgres-artifacts | Implement PostgreSQL and durable artifacts. | remote-decisions |
| entra-mcp-auth | Implement MCP OAuth/Entra validation and delegation. | remote-decisions |
| human-web-auth | Implement secure human sessions and CSRF. | remote-decisions |
| hosted-worker | Deploy the separately managed owner/policy-aware worker. | postgres-artifacts |
| remote-observability | Add safe logs, traces and dashboards. | hosted-worker; entra-mcp-auth |
| remote-gate-c | Repeat performance, payload and admission proof remotely. | All Gate D work |
| live-one-profile | Run the authorised 13-operation canary. | Gate D; live authority |
| live-three-profile | Run the authorised 23-operation canary. | One-profile acceptance |
| release-decision | Select shared, narrowed, read-only or stopped mode. | Canary evidence |

# First Day for the Next Developer

| Step | Action |
| --- | --- |
| 1 | Read geo-agent-mcp-next-gates-plan.md, geo-agent/AGENTS.md and geo-agent/README.md. |
| 2 | Confirm the branch contains the MCP implementation commit and the worktree is clean. |
| 3 | Run the workspace and end-to-end verifiers, then confirm the 612-test baseline before Gate D. |
| 4 | Run the browser harness and tests/measure_mcp_performance.py before infrastructure changes. |
| 5 | Inspect mcp_server.py, measurement_service.py, agent_access.py, persistence.py, worker.py, api.py and live_runtime.py. |
| 6 | Close the interactive Gate C.5 check before provisioning any Azure resource. |
| 7 | Keep GEO_MCP_ALLOW_LIVE false until Gate D passes and Gate E is separately authorised. |

# Source Links

Authoritative Markdown handoff

GEO agent README

MCP server

Shared application service

Persistence and lifecycle

Local performance baseline

Official Python MCP SDK

Microsoft Foundry MCP guidance

Recommendation: proceed with Gate D only after the interactive Gate C.5 check passes and the platform owner approves the environment and identity model. Do not provision live capacity or enable live MCP until Gate D passes and Gate E has written authorisation.